## Mission-HA - Sprint Planning
SPRINT PLANNING GROUP 7
PROJECT NAME |  |  |  | PROJECT MANAGER |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE | Team Menbers: Darren, Jimmy, Jeff Hobbs, Mohammad Jalal, Sushma
Mission: (Highly) Available! |  |  |  | Kent Burgdorfer |  | 2025-04-22 | 2025-05-20 |  | SCOPE STATEMENT | Jill Power
At Risk? | TASK NAME | Deliverables | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
| SPRINT 1 : Sprint Plan |  |  |  |  | 2025-04-22 | 04/24/20256 | #VALUE!
| Task 1 | Defining Team Roles |  | Team |  | 2025-04-22 | 2025-04-24 | 3 | Complete
| Task 2 | Write User Stories and acceptance criteria |  | Sushma |  |  |  |  | Complete
| Task 3 | Breakdown tasks into backlog items |  | Team |  |  |  |  | Complete
| Task 4 | Create a timeline and assign responsibilities |  | Team |  |  |  |  | Complete
| Task 5 | AWS Account |  | All |  |  |  |  | Complete |  | Everyone will test in their individual accounts
| Task 6 | Sprint Plan Document |  | Darren |  |  |  |  | Complete
| Task 7 | Set up GitHub/GitLab repo |  | Sushma |  |  |  |  | Complete
| Task 8 | Choosing Project management tool |  | Team |  |  |  |  | Complete |  | Google Docs
| SPRINT 2: CloudFormation Template (IaC) |  |  |  |  | 2025-04-25 | 2025-04-29 | 5
| Task 1 | Identifies and specifies the necessary resources for implementing a high availability (HA) architecture |  | Team |  | 2025-04-25 | 2025-04-25 | -45771 | Complete
| Task 2 | Design logical architecture(VPC, EC2, RDS etc) |  | Team |  |  |  |  | Complete
| Task 3 | Create modular CloudFormation templates |  | Jimmy |  |  |  |  | Complete
| Task 4 | Inline comments in templates and add to GitHub with README version 1 | [6 empty] | Complete
| Task 5 | Deploys Primary Region N-Tier architecture (YAML or JSON with README.md) |  | Team |  |  |  |  | Complete
| Task 6 | Test stack deployment and parameterization |  | Mohammad |  |  |  |  | Complete
| SPRINT 3 : Primary Region Deployment |  |  |  |  | 2025-04-30 | 2025-05-06 | 7
| Task 1 | Deploys all stacks using CloudFormation |  |  |  | 2025-04-30 | 2025-05-06 | 7 | Complete
| Task 2 | Confirm full connectivity: Web/App <->RDS |  | Jimmy |  |  |  |  | Complete
| Task 3 | Add sample front-end content and DB entries |  | Jimmy |  |  |  |  | Complete
| Task 4 | Test Functional web app with RDS backend in primary region (demo or screenshot) | [6 empty] | In Progress
| SPRINT 4 : DR Region Deployment | [5 empty] | 2025-05-13
| Task 1 | Deployed DR stack with DNS/manual failover demonstration |  |  |  | 2025-05-07 | 2025-05-13 | 7 | In Progress
| Task 2 | Replicate and modify templates for DR region | [6 empty] | In Progress
| Task 3 | Create cross-region RDS read replica | [6 empty] | In Progress
| Task 4 | Deploy Web/App tiers in DR region | [6 empty] | In Progress
| Task 5 | Set up Route 53 with health checks and failover policy | [6 empty] | In Progress
| Task 6 | Simulate failure and verify auto redirection | [6 empty] | In Progress
| Task 7 | Document RPO/RTO and capture failure proof (Video/screenshots) | [6 empty] | In Progress
| SPRINT 5 : Final Submission & Presentation |  |  |  |  | 2025-05-14 | 2025-05-20 | 7
| Task 1 | Clean and organize all CloudFormation templates | [6 empty] | In Progress
| Task 2 | Finalize README.md and code comments | [6 empty] | In Progress
| Task 3 | Create architecture diagram (Lucidchart/draw.io) | [6 empty] | In Progress
| Task 4 | Record a 5-minute team presentation or slide deck | [6 empty] | In Progress
| Task 5 | Write final summary report | [6 empty] | In Progress
| Task 6 | Submit GitHub repo, demo media, and final documentation | [6 empty] | In Progress
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*